## Action Items
Action Items
Project Name
MM/DD/YYYY
ID | Who | Will do what | Date assigned | Due date | Status
[5 empty] | Color | Notes
1 | Erica Example | Send out meeting invite | 2023-09-25 | 2023-10-02 | G
2 |  |  |  |  | R
3 |  |  |  |  | G
4 |  |  |  |  | C
5 |  |  |  |  | G
6 |  |  |  |  | R
7 |  |  |  |  | C
8 |  |  |  |  | G
9 |  |  |  |  | G
10 |  |  |  |  | G
Status Key - Colors
| G | Going/Controlled – Task is on schedule
| R | Critical – Task has fallen significantly behind schedule, has encountered a major problem/risk, or has taken on other tasks that are out of scope.
| C | Complete.
| ? | Status unknown.

## Template instructions
How to update the action item list, decision log and parking lot
During the meetings: share your screen to display Action Item file
Action Items:
Step | Task
1 | Review action items with meeting attendees starting at the top of the list.
2 | Ask the person listed in the "who" column for a status on each item.
3 | If the item is completed, mark it complete (C) in the F column.
4 | If the item is not completed, find out why. In the G column, add today's date and notes about the update
If responsible party is not present, mark R(red) to remind you to follow up with that person later or at next meeting.
5 | For new action items that are not updates of already captured tasks, add to the bottom of the list.
Confirm your description of the item with the group to ensure you captured it correctly.
Ask the group who will be primary responsibility for ensure the task is completed and when the item should be due.
Ask the group if there are any communication pieces that need to take place in regards to the action item.
Try to avoid a "TBD" item on any list. Instead list a date to revisit the task, even if it is just to "check in".
6 | Update each new and existing action item to reflect the new status.
"R" indicates the item is overdue and should automatically turn the cell red.
"C" indicates the item is complete and should automatically turn the cell blue.
"G" indicates the item is on track and should automatically turn the cell green.
Decision Log:
1 | For each decision that is made, confirm the decision with the group and ask for a vote if appropriate.
2 | Write the decision down in Decision Log tab
3 | For each decision, be sure to capture any notes that are needed, and any communication assignments that need to be completed as a result of the decision.
Parking Lot:
If the group finds an action item they do not want to take action on immediately but would like to revisit in the future, confirm this with the team and then write it down for the parking lot. Be sure to capture a date to return to the item.
Lessons Learned:
If the group appears to be agreeing on a lessons learned" item, ask for consensus. If the team agrees, write it down for the lessons learned log.
After the meetings:
Step | Task
1 | Save file with current meeting date at top (row 3)
2 | For each item that has turned "C" for complete, right click on the row on the left side panel of the screen to highlight then entire row. Click "hide". The row should disappear. This allows us to retain all completed items without them cluttering the working document.
3 | If using written notes, update the document with new information for each item on the appropriate tab.
4 | Keep all items in chronological order (earliest date at the top of the list). This may require you to cut and paste the tasks to get them in the proper order.
5 | Send updated Action Items file to attendees along with any other documents as needed.

## Decision Log
Decision Log
Project Name
MM/DD/YYYY
ID | Decision | Date made | Keywords
1
2
3
4
5
6
7
8
9
10

## Parking Lot
Parking Lot
Project Name
MM/DD/YYYY
ID | Description | Who identified? | Date identified | Revisit when? | Outcome
1 | 360 degree reviews – determine if we have capacity to do this yet. | Steve R. (lead) with Steve A. and Blake | 2014-03-01 | 2014-08-01

## Lessons Learned
Lessons Learned Log
Project Name
MM/DD/YYYY
ID | Lesson | Date captured | Keywords
1
2
3
4
5
6
7
8
9
10